## Project Plan and Gantt
Project Name: | [Name]
Report Date | [Date]
Project Status | On track
Completed | 27%
Tasks | Assigned To | Priority | Status
Set kick-off meeting | Alex B. |  | Complete
Agree on objectives | Frank C. | ★ | Complete
Detailed Reqs. | Jacob S. |  | Complete
Hardward Reqs. | Jacob S. | ★ | Overdue
Final Resource Plan | Jacob S. |  | In progress
Staffing | Alex B. | ★ | In progress
Techincal Reqs. | Frank C. |  | Not started
Testing | Kennedy K. | ★ | Not started
Dev. Complete | Jacob S. | ★ | Not started
Hardware Config. | Alex B. |  | Not started
System Testing | Kennedy K. | ★ | Not started
Launch
Or, Click Here to Get Our Project Management Solution in Smartsheet

## Notes
Task Table
Tasks | Assigned To | Start | End | Days | Status
Set kick-off meeting | Alex B. | 2015-09-02 | 2015-09-03 | 1 | Complete
Agree on objectives | Frank C. | 2015-09-03 | 2015-09-07 | 4 | Complete
Detailed Reqs. | Jacob S. | 2015-09-07 | 2015-09-12 | 5 | Complete
Hardward Reqs. | Jacob S. | 2015-09-09 | 2015-09-11 | 2 | Overdue
Final Resource Plan | Jacob S. | 2015-09-11 | 2015-09-15 | 4 | In progress
Staffing | Alex B. | 2015-09-16 | 2015-09-17 | 1 | In progress
Techincal Reqs. | Frank C. | 2015-09-17 | 2015-09-21 | 4 | Not started
Testing | Kennedy K. | 2015-09-24 | 2015-10-02 | 8 | Not started
Dev. Complete | Jacob S. | 2015-10-02 | 2015-10-05 | 3 | Not started
Hardware Config. | Alex B. | 2015-10-05 | 2015-10-07 | 2 | Not started
System Testing | Kennedy K. | 2015-10-06 | 2015-10-09 | 3 | Not started
Launch |  | 2015-10-09 | 2015-10-10 | 1
Percentage of Tasks Complete
Complete | 27.27%
Overdue | 9.091%
In progress | 18.18%
Not Started | 45.45%
Budget
Planned | 80000
Actual | 50000
Pending Items
Decisions | 5
Actions | 2
Change Requests | 4